## Instructions
Cyber Risk Register
First National Bank (Fictional) — simulated data for portfolio demonstration
How to use | Add one row per risk on the Risk Register sheet. Grey columns calculate automatically — do not type over them.
Column | What it means
Risk ID | Unique identifier, e.g. R-001. Keep it stable once issued.
Risk Title | One line naming the risk event, not the control gap.
Threat Source | Who or what causes it: external attacker, insider, vendor, system failure.
Asset / Process | What is affected — the system, data set or business process.
Likelihood (1-5) | 1 Rare · 2 Unlikely · 3 Possible · 4 Likely · 5 Almost certain.
Impact (1-5) | 1 Negligible · 2 Minor · 3 Moderate · 4 Major · 5 Severe.
Inherent Risk | CALCULATED: Likelihood × Impact, before controls.
Inherent Rating | CALCULATED: 15+ Critical · 10-14 High · 5-9 Medium · below 5 Low.
Existing Controls | Controls already operating against this risk.
Control Effectiveness % | How much of the risk those controls remove. Evidence-based where possible; state the basis in Treatment Plan if assumed.
Residual Risk | CALCULATED: Inherent Risk × (1 − Control Effectiveness).
Residual Rating | CALCULATED on the same bands as Inherent Rating.
Risk Owner | The named accountable person. Not a team.
Treatment | Accept · Mitigate · Transfer · Avoid.
Treatment Plan | What will be done, by whom. Specific enough to track.
Target Date | When the treatment completes.
Status | Open · In Progress · Monitoring · Closed.
ALE (FAIR, $) | Annualised loss expectancy from the quantitative risk engine, where the risk has been modelled.
NIST CSF 2.0 Ref | Relevant CSF 2.0 subcategory, e.g. GV.PO-01.
OSFI Ref | Relevant OSFI guideline: B-10, B-13 or E-21.
Rating bands | Critical 15-25 · High 10-14 · Medium 5-9 · Low 1-4
Note on the examples | The five pre-filled rows are the modelled FAIR scenarios. Their ALE figures come from the quantitative risk engine. Replace or extend them.

## Risk Register
Risk ID | Risk Title | Threat Source | Asset / Process | Likelihood (1-5) | Impact (1-5) | Inherent Risk | Inherent Rating | Existing Controls | Control Effectiveness % | Residual Risk | Residual Rating | Risk Owner | Treatment | Treatment Plan | Target Date | Status | ALE (FAIR, $) | NIST CSF 2.0 Ref | OSFI Ref
R-001 | Ransomware Attack | External attacker | Core banking platform | 4 | 5 |  |  | Immutable offline backups with quarterly restore testing; Network segmentation limiting lateral movement; Endpoint detection and response deployed fleet-wide; Ransomware-specific incident response playbook | 75% |  |  | CISO | Mitigate | Implement recommended controls (annual cost $500,000). | 2027-03-31 | Open | 5448306 | PR.AA-03, DE.CM-01, RC.RP-01 | OSFI E-21 Operational Resilience; B-13 Technology Operations and Resilience
R-002 | Data Breach — Customer PII | External attacker | Customer PII datastore | 4 | 5 |  |  | Data loss prevention tooling across email and endpoint; AES-256 encryption at rest and TLS 1.2+ in transit for all PII; Privileged access management with session recording; Documented OSFI 24-hour breach notification procedure | 70% |  |  | CISO | Mitigate | Implement recommended controls (annual cost $350,000). | 2027-03-31 | Open | 4991621 | PR.DS-01, DE.CM-01, RS.MA-01 | OSFI Technology and Cyber Security Incident Reporting Advisory (24-hour notification)
R-003 | Cloud Misconfiguration — Data Exposure | Internal misconfiguration | Cloud storage and IAM | 5 | 4 |  |  | Cloud security posture management with continuous scanning; Infrastructure-as-code security scanning in the CI/CD pipeline; Policy-enforced prohibition on public storage buckets; Automated secret detection across all repositories | 80% |  |  | CISO | Mitigate | Implement recommended controls (annual cost $180,000). | 2027-03-31 | Open | 4462175 | PR.DS-01, ID.AM-01, DE.CM-01 | OSFI B-13 Technology Operations and Resilience (cloud risk)
R-004 | Third-Party Vendor Security Failure | Third-party provider | Critical vendor services | 3 | 4 |  |  | Risk-tiered vendor security questionnaires before onboarding; Contractual security requirements including 24-hour breach notification; Continuous monitoring with tier-based reassessment cycles; Documented exit strategy for every critical vendor | 65% |  |  | CISO | Mitigate | Implement recommended controls (annual cost $200,000). | 2027-03-31 | Open | 2677779 | GV.SC-01, ID.RA-01, RS.CO-02 | OSFI B-10 Third-Party Risk Management
R-005 | Insider Threat — Privileged Access Abuse | Malicious or negligent insider | Privileged access to customer records | 3 | 4 |  |  | User and entity behaviour analytics on privileged accounts; Least-privilege access with quarterly recertification; Separation of duties on high-value transactions; Same-day access revocation on offboarding | 60% |  |  | CISO | Mitigate | Implement recommended controls (annual cost $280,000). | 2027-03-31 | Open | 2034581 | PR.AA-01, DE.AE-02, RS.MA-01 | OSFI B-13 Cyber Security (access management)